## Ralph Granata
To-do list
To be completed by: |  |  |  | Name: Ralph Granata
Deadline: |  |  |  | Date: 12/07/2023
Group 3 Midterm 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | (Group) Planning & Strategy | 2023-11-20 | 2023-11-21 |  | 1
100% | (Individual) Model Revision for Group Starting Model: Template, Domains, Sequences, Validations, Themes, Normalization. | 2023-11-21 | 2023-11-24 | 2023-11-27 | 6 | Model updates took longer than expected, trying to accommodate data
100% | (Group) Model Selection, Merge & Update: Complete SQLServer2019 Model | 2023-11-27 | 2023-12-02 | 2023-12-05 | 8 | Many updates needed to be made to both the model and data as we were learning about triggers and functions
100% | (Individual) Data Insertion Revisions | 2023-11-27 | 2023-12-05 |  | 2 | Updated in conjunction with model
100% | (SubTeams) PG Model: Convert SQL Server model and fully implement in PostgreSQL | 2023-12-03 | 2023-12-05 |  | 2
100% | (Individiual) Presentation | 2023-12-05 | 2023-12-06 |  | 1
0% | VHDX Submission: Backup all dbs, documents, models, etc. for blackboard submission | 2023-12-06 | 2023-12-07 |  | 1

## Savaze Khattak
To-do list
To be completed by: |  |  |  | Name: Savaze Khattak
Deadline: |  |  |  | Date: 12/07/2023
Group 3 Midterm 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | (Group) Planning & Strategy | 2023-11-20 | 2023-11-21 |  | 1
100% | (Individual) Model Revision for Group Starting Model: Template, Domains, Sequences, Validations, Themes, Normalization. | 2023-11-21 | 2023-11-24 |  | 6
100% | (Group) Model Selection, Merge & Update: Complete SQLServer2019 Model | 2023-11-27 | 2023-12-02 | 2023-12-05 | 8 | Many updates needed to be made to both the model and data as we were learning about triggers and functions
100% | (SubTeams) PG Model: Convert SQL Server model and fully implement in PostgreSQL | 2023-12-03 | 2023-12-05 |  | 2
100% | (Individiual) Presentation | 2023-12-05 | 2023-12-06 |  | 1

## Mehrshad Eshaghianpour
To-do list
To be completed by: |  |  |  | Name: Mehrshad Eshaghianpour
Deadline: |  |  |  | Date: 12/07/2023
Group 3 Midterm 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | (Group) Planning & Strategy | 2023-11-20 | 2023-11-21 |  | 1
100% | (Individual) Model Revision for Group Starting Model: Template, Domains, Sequences, Validations, Themes, Normalization. | 2023-11-21 | 2023-11-24 | 2023-12-25 | 6
100% | (Group) Model Selection, Merge & Update: Complete SQLServer2019 Model | 2023-11-27 | 2023-12-02 | 2023-12-05 | 8 | Many updates needed to be made to both the model and data as we were learning about triggers and functions
100% | (Subteams) MySQL Model: Convert SQL Server model and fully implement in MySQL | 2023-12-03 | 2023-12-06 |  | 3
100% | (Individiual) Presentation | 2023-12-05 | 2023-12-06 |  | 1

## Jimmy Puli
To-do list
To be completed by: |  |  |  | Name: Jimmy Puli
Deadline: |  |  |  | Date: 12/07/2023
Group 3 Midterm 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | (Group) Planning & Strategy | 2023-11-20 | 2023-11-21 |  | 1
100% | (Individual) Model Revision for Group Starting Model: Template, Domains, Sequences, Validations, Themes, Normalization. | 2023-11-21 | 2023-11-24 |  | 6
100% | (Group) Model Selection, Merge & Update: Complete SQLServer2019 Model | 2023-11-27 | 2023-12-02 | 2023-12-05 | 8 | Many updates needed to be made to both the model and data as we were learning about triggers and functions
100% | (Subteams) MySQL Model: Convert SQL Server model and fully implement in MySQL | 2023-12-03 | 2023-12-06 |  | 3
100% | (Individiual) Presentation | 2023-12-05 | 2023-12-06 |  | 1

## Chuan Chen
To-do list
To be completed by: |  |  |  | Name: Chuan Chen
Deadline: |  |  |  | Date: 12/07/2023
Group 3 Midterm 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | (Group) Planning & Strategy | 2023-11-20 | 2023-11-21 | 2023-11-26 | 1
100% | (Individual) Model Revision for Group Starting Model: Template, Domains, Sequences, Validations, Themes, Normalization. | 2023-11-21 | 2023-11-24 | 2023-11-28 | 6
100% | (Group) Model Selection, Merge & Update: Complete SQLServer2019 Model | 2023-11-27 | 2023-12-02 | 2023-12-05 | 8 | Many updates needed to be made to both the model and data as we were learning about triggers and functions
100% | (Subteams) Mongo Model: Convert SQL Server model and fully implement in MongoDB | 2023-12-03 | 2023-12-06 | 2023-12-07 | 3 | Migrated from SQL to MongoDB
100% | (Individiual) Presentation | 2023-12-05 | 2023-12-06 | 2023-12-07 | 1 | Created MongoDB Presentation

## Kenneth Hasiholan
To-do list
To be completed by: |  |  |  | Name: Kenneth Hasiholan
Deadline: |  |  |  | Date: 12/07/2023
Group 3 Midterm 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | (Group) Planning & Strategy | 2023-11-20 | 2023-11-21 |  | 1
100% | (Individual) Model Revision for Group Starting Model: Template, Domains, Sequences, Validations, Themes, Normalization. | 2023-11-21 | 2023-11-24 |  | 6
100% | (Group) Model Selection, Merge & Update: Complete SQLServer2019 Model | 2023-11-27 | 2023-12-02 | 2023-12-05 | 8 | Many updates needed to be made to both the model and data as we were learning about triggers and functions
100% | (Subteams) Mongo Model: Convert SQL Server model and fully implement in MongoDB | 2023-12-03 | 2023-12-06 |  | 3
100% | (Individiual) Presentation | 2023-12-05 | 2023-12-06 |  | 1

## Ryan King
To-do list
To be completed by: |  |  |  | Name: Ryan King
Deadline: |  |  |  | Date: 12/07/2023
Group 3 Midterm 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | (Group) Planning & Strategy | 2023-11-20 | 2023-11-21 |  | 1
100% | (Individual) Model Revision for Group Starting Model: Template, Domains, Sequences, Validations, Themes, Normalization. | 2023-11-21 | 2023-11-24 |  | 6
100% | (Group) Model Selection, Merge & Update: Complete SQLServer2019 Model | 2023-11-27 | 2023-12-02 | 2023-12-05 | 8 | Many updates needed to be made to both the model and data as we were learning about triggers and functions
100% | (Individual) Mongo Model: Convert SQL Server model and fully implement in MongoDB | 2023-12-03 | 2023-12-06 |  | 3
100% | (Individiual) Presentation | 2023-12-05 | 2023-12-06 |  | 1